## Test Execution Log
PRACTICAL 6 — MANUAL TEST EXECUTION LOG
Execution-Oriented Regression Cycle — Login Module, practice.expandtesting.com
Application Under Test: |  |  | Expand Testing Practice Login Page (https://practice.expandtesting.com/login)
Module Scope: |  |  | Authentication / Login Module — full regression execution cycle
Test Cycle: |  |  | Regression Cycle R1 — Manual Test Execution
Executed By: |  |  | Abhishek
Test Environment: |  |  | Windows 11, Google Chrome (Latest) — Manual Black Box Testing
Valid Test Credentials: |  |  | Username: practice ¦ Password: SuperSecretPassword!
Execution Window: |  |  | 28-Jul-2026 to 29-Jul-2026
Test Case ID | Requirement ID | Module | Priority | Severity | Preconditions | Test Data | Steps | Expected Result | Actual Result | Execution Status | Tester | Execution Date | Environment | Remarks
TC_EXEC_01 | REQ_LOGIN_01 | Functional | High | Medium | Application URL is accessible | practice / SuperSecretPassword! | 1. Open Login Page 2. Enter Username 3. Enter Password 4. Click Login 5. Verify successful login | User is redirected to /secure with a success message | User redirected to /secure with 'You logged into a secure area!' message | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Baseline case — corresponds to TC_LOGIN_01 in the source Practical 6 artifact
TC_EXEC_02 | REQ_LOGIN_02 | Functional | High | High | Application URL is accessible | wrongUser / SuperSecretPassword! | 1. Open Login Page 2. Enter an invalid username 3. Enter the valid password 4. Click Login 5. Observe message | 'Invalid username.' displayed; user remains on /login | 'Invalid username.' displayed as expected | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_03 | REQ_LOGIN_03 | Functional | High | High | Application URL is accessible | practice / WrongPassword | 1. Open Login Page 2. Enter the valid username 3. Enter an incorrect password 4. Click Login 5. Observe message | 'Invalid password.' displayed; user remains on /login | 'Invalid password.' displayed as expected | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_04 | REQ_LOGIN_04 | Boundary | Medium | Low | Application URL is accessible | (blank) / SuperSecretPassword! | 1. Leave Username blank 2. Enter the valid password 3. Click Login 4. Observe result | An inline validation cue appears before submission | No inline cue shown; server returns 'Invalid username.' after full round trip | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-001 (Practical 5); recurring, no fix deployed yet
TC_EXEC_05 | REQ_LOGIN_04 | Boundary | Medium | Low | Application URL is accessible | practice / (blank) | 1. Enter the valid username 2. Leave Password blank 3. Click Login 4. Observe result | An inline validation cue appears before submission | No inline cue shown; server returns 'Invalid password.' after full round trip | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-001 (Practical 5); same root cause as TC_EXEC_04
TC_EXEC_06 | REQ_LOGIN_04 | Boundary | Low | Low | Application URL is accessible | (blank) / (blank) | 1. Leave both fields blank 2. Click Login 3. Observe result | Login rejected gracefully with no unhandled exception | Rejected with 'Invalid username.'; no application error | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Server-side handling itself is correct; only the inline-validation gap (BUG-001) is open
TC_EXEC_07 | REQ_LOGIN_05 | Boundary | Medium | Low | Application URL is accessible | 300-character string / SuperSecretPassword! | 1. Enter a 300-character string into Username 2. Enter the valid password 3. Click Login 4. Inspect Username field for a maxlength attribute | Field enforces a reasonable maxlength or rejects gracefully | No maxlength attribute present; rejected gracefully as 'Invalid username.' | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-005 (Practical 5); recurring since Practical 2 (BUG-LOGIN-01) — third consecutive cycle observed
TC_EXEC_08 | REQ_LOGIN_06 | Negative | Medium | Medium | Application URL is accessible | prac!@#$%^&*() / SuperSecretPassword! | 1. Enter a username with special characters 2. Enter the valid password 3. Click Login 4. Observe result | Login rejected gracefully; no crash | Rejected with 'Invalid username.'; no crash observed | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_09 | REQ_LOGIN_07 | Security | High | Critical | Application URL is accessible | ' OR '1'='1 / SuperSecretPassword! | 1. Enter a safe SQL-injection-style string into Username 2. Click Login 3. Observe whether authentication is bypassed | No authentication bypass; payload treated as literal text | Rejected with 'Invalid username.'; no bypass observed | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Syntax-only input; no exploitation attempted
TC_EXEC_10 | REQ_LOGIN_08 | Security | High | High | Application URL is accessible | <script>alert('xss')</script> / SuperSecretPassword! | 1. Enter a script-tag XSS-style string into Username 2. Click Login 3. Observe whether the script executes | No script executes; payload not reflected unescaped | No alert/script execution observed; rejected as 'Invalid username.' | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_11 | REQ_LOGIN_09 | UI | Medium | Low | Application URL is accessible | Password: SuperSecretPassword! | 1. Click into Password field 2. Type password 3. Confirm characters mask as dots | Characters mask as typed | Characters masked correctly | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_12 | REQ_LOGIN_10 | UI | Low | Low | Application URL is accessible | Password: SuperSecretPassword! | 1. Type a password 2. Look for a show/hide toggle icon | Optional toggle icon present | No toggle icon present | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-003 (Practical 5); usability enhancement, not functional defect
TC_EXEC_13 | REQ_LOGIN_11 | Navigation | Medium | Medium | Focus is at the top of the login page | practice / SuperSecretPassword! | 1. Tab through Username, Password, Login button 2. Submit using Enter from the Password field | Logical Tab order; form fully keyboard-operable | Tab order logical; Enter submitted the form successfully | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_14 | REQ_LOGIN_12 | Session | High | Medium | User is logged in and on /secure | N/A | 1. Refresh the page (F5) 2. Observe whether session persists | Session persists; /secure content remains visible | Session persisted correctly after refresh | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_15 | REQ_LOGIN_13 | Session | High | Medium | User is logged in and on /secure | N/A | 1. Click Logout 2. Observe resulting page and session state | User returned to /login; session terminated | User returned to /login; session terminated correctly | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_16 | REQ_LOGIN_14 | Security | Medium | Low | Application URL is accessible | practice / WrongPass1...5, then SuperSecretPassword! | 1. Submit 5 consecutive incorrect passwords 2. Attempt a 6th login with correct password 3. Observe lockout behaviour | Temporary lockout, delay or CAPTCHA expected on a production system | No lockout triggered; 6th attempt with correct credentials succeeded immediately | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-002 (Practical 5); acceptable for a demo environment, flagged as hardening observation
TC_EXEC_17 | REQ_LOGIN_15 | Access Control | High | High | Fresh session, no prior login | Direct URL: /secure | 1. Navigate directly to /secure without logging in 2. Observe result | Access blocked or redirected to /login | Redirected to /login; protected content not rendered | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_18 | REQ_LOGIN_16 | Navigation | Low | Low | User is logged in and on /secure | Direct URL: /login | 1. While authenticated, navigate to /login directly 2. Observe whether redirected to /secure or form re-shown | Redirect to /secure expected | Login form re-displayed instead of redirecting | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-006 (Practical 5); not a security defect
TC_EXEC_19 | REQ_LOGIN_17 | Responsive | Medium | Low | Browser DevTools device emulation available | Viewport: 375x667 | 1. Load login page at 375x667 mobile viewport 2. Verify form reflows without horizontal scroll | Form reflows to a mobile-friendly single-column layout | Layout reflowed correctly; no horizontal scroll observed | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_20 | REQ_LOGIN_17 | Responsive | Low | Low | Browser DevTools device emulation available | Viewport: 300x640 | 1. Set viewport width to 300px 2. Inspect field/button spacing versus desktop layout | Consistent, comfortable spacing retained | Spacing appears noticeably tighter than desktop view | Fail | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Linked to BUG-004 (Practical 5); cosmetic only
TC_EXEC_21 | REQ_LOGIN_18 | Compatibility | High | Medium | Google Chrome installed | N/A | 1. Exercise the full login flow in Chrome 2. Confirm layout and functional behaviour | Page renders and functions correctly | Layout, fonts and functional behaviour rendered correctly | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_22 | REQ_LOGIN_18 | Compatibility | Medium | Medium | macOS device with Safari installed | N/A | 1. Exercise the full login flow in Safari on macOS 2. Compare against the Chrome baseline (TC_EXEC_21) | Consistent rendering and behaviour with the Chrome baseline | Not executed — no macOS/Safari environment was available in this test cycle | Blocked | Abhishek | 28-Jul-2026 | macOS, Safari (Unavailable) | Blocked — environment not provisioned for this cycle; carried forward to Regression Cycle R2
TC_EXEC_23 | REQ_LOGIN_19 | Security | Medium | Medium | Application URL is accessible | N/A | 1. Inspect connection/protocol in DevTools 2. Confirm HTTPS with a valid TLS certificate | Page served over HTTPS with a valid TLS certificate | Confirmed HTTPS with a valid TLS certificate; no mixed-content warnings | Pass | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_24 | REQ_LOGIN_19 | Security | Medium | Medium | Server-side password storage mechanism | N/A — requires backend access | 1. Attempt to verify the password hashing/storage algorithm used server-side 2. Determine whether this is observable via black-box testing alone | Password storage mechanism should be verifiable as part of a full security assessment | Not executed — server-side implementation is not accessible to a black-box tester; requires source-code or infrastructure access outside this engagement's scope | Blocked | Abhishek | 28-Jul-2026 | Windows 11, Google Chrome (Latest) | Blocked — outside black-box testing scope; recommend a dedicated backend security review by the development team
TC_EXEC_25 | REQ_LOGIN_20 | Functional | Medium | Low | Application URL is accessible | ' practice ' / SuperSecretPassword! | 1. Enter the valid username with leading/trailing whitespace 2. Enter the valid password 3. Click Login 4. Observe whether input is trimmed | Behaviour should be consistent, whether trimmed or treated as distinct | Rejected as 'Invalid username.'; value is not trimmed before comparison | Pass | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | No functional defect; behaviour undocumented but safe
TC_EXEC_26 | REQ_LOGIN_21 | Error Handling | Medium | Low | Application URL is accessible | practice / SuperSecretPassword! | 1. Enter valid credentials 2. Rapidly double-click Login 3. Observe for duplicate request/error | No duplicate-submission side effect | No duplicate message or error occurred; fast redirect absorbed the second click | Pass | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_27 | REQ_LOGIN_22 | Accessibility | Medium | Low | Application URL is accessible | N/A | 1. Inspect Username/Password inputs for associated labels 2. Confirm Login button has an accessible name 3. Verify visible focus indicator on Tab | Inputs labelled; button has accessible name; focus visible | Inputs labelled correctly; accessible name confirmed; focus outline visible | Pass | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | Spot-check only, not a full WCAG 2.1 AA audit
TC_EXEC_28 | REQ_LOGIN_22 | Accessibility | Low | Low | Application URL is accessible | N/A | 1. Perform a full automated WCAG 2.1 AA conformance scan (e.g. axe-core) across the login page 2. Review colour contrast, ARIA roles, and screen-reader announcement order in full | Comprehensive accessibility conformance results, beyond the spot-check in TC_EXEC_27 | Not executed this cycle — deferred to a dedicated accessibility-audit cycle with the appropriate tooling and specialist review | Deferred | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | Deferred — scheduled for a dedicated accessibility audit cycle, out of scope for this regression pass
TC_EXEC_29 | REQ_LOGIN_23 | Performance | Medium | Low | DevTools Network tab open | N/A | 1. Reload /login with Network recording 2. Record page load time and total request count | Page loads within 3 seconds with a lightweight resource footprint | Page loaded in approximately 1.1 seconds with a lightweight resource footprint | Pass | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_30 | REQ_LOGIN_23 | Performance | Low | Low | Load-testing tool and staging environment required | N/A | 1. Simulate concurrent multi-user login load against the application 2. Measure response time degradation under load | Application maintains acceptable response times under a defined concurrent-user load | Not executed — load-testing tooling and a non-production target environment are required and were not available in this cycle | Deferred | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | Deferred — recommend a dedicated performance/load-testing cycle against a staging environment, not the shared public demo instance
TC_EXEC_31 | REQ_LOGIN_24 | Functional | Medium | Medium | Application URL is accessible | Invalid username and invalid password scenarios | 1. Trigger both invalid-username and invalid-password scenarios 2. Assess clarity, wording and placement of each message | Error messages are clear, field-specific, and prominently placed | Messages are clear, field-specific, and placed directly above the form | Pass | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | -
TC_EXEC_32 | REQ_LOGIN_25 | Process Integrity | Medium | Low | All test cases in this execution log have been run or dispositioned | TC_EXEC_01–TC_EXEC_31 execution results | 1. Cross-check every Fail-status case against its linked Bug ID 2. Confirm every Blocked/Deferred case has a documented reason and follow-up plan | Full traceability with no undocumented Blocked or Deferred case, and every Fail linked to a known defect | All 6 Fail cases trace to BUG-001–BUG-006 (Practical 5); both Blocked cases and both Deferred cases carry a documented reason and follow-up plan | Pass | Abhishek | 29-Jul-2026 | Windows 11, Google Chrome (Latest) | Execution-log integrity check; confirms this cycle's Test Execution Report is fully grounded

## Execution Summary
PRACTICAL 6 — TEST EXECUTION METRICS
Application: | practice.expandtesting.com/login
Total Test Cases: | 32
Execution Status | Count | % of Total
Pass | 21 | 65.62%
Fail | 7 | 21.88%
Blocked | 2 | 6.25%
Deferred | 2 | 6.25%
Not Executed | 0 | 0%
Pass Rate (of Executed, excl. Blocked/Deferred) | 75%
Module | Total | Pass | Fail
Functional | 5 | 5 | 0
Boundary | 4 | 1 | 3
Negative | 1 | 1 | 0
Security | 5 | 3 | 1
UI | 2 | 1 | 1
Navigation | 2 | 1 | 1
Session | 2 | 2 | 0
Access Control | 1 | 1 | 0
Responsive | 2 | 1 | 1
Compatibility | 2 | 1 | 0
Error Handling | 1 | 1 | 0
Accessibility | 2 | 1 | 0
Performance | 2 | 1 | 0
Process Integrity | 1 | 1 | 0